1. Project Title
The "Tisankhe!" (Let Us Choose!) Project: Dismantling Stigma, Empowering Youth in SRMNCAH in Machinga District, Malawi.

2. Applicant Information

| Name of Organization | Mthunzi Trust |
| --- | --- |
| Address | P. O. Box 12, Chileka, Blantyre, Malawi. |
| Telephone | +265 996 654 088 |
| Email | mthunzitrust.mw@gmail.com |
| Contact Person | Name: Joel Chirwa Designation: Grants & Partnerships Officer Email: chirwajj@gmail.com |

3. Project Summary

Mthunzi Trust proposes the "Tisankhe!" Project, a 15-month initiative to address the critical barrier of socio-cultural stigma preventing youth in Machinga District from accessing SRMNCAH services. The project will directly empower 500 young people (15-24 years) and engage 50 community gatekeepers in Traditional Authority Ngokwe. Key activities include training 30 youth peer educators, conducting community dialogues with traditional leaders, and launching a youth-friendly IEC campaign. Expected outcomes include a 40% increase in youth confidence to access SRMNCAH services and the establishment of sustainable peer-support networks, leading to reduced early pregnancies and improved adolescent health.

4. Background and Problem Statement

Malawi faces a crisis in adolescent health, with a national adolescent birth rate of 136 per 1,000 women. This is most acute in Machinga District, which has the highest rate in the country at 177 (Malawi DHS 2015-16). This high rate is a direct result of unmet need for family planning, driven not by a lack of services, but by pervasive cultural stigma and taboos. Young people, especially girls, face discrimination when seeking information on contraception and STI screening, leading to secrecy and unsafe practices. This project directly aligns with CORE Group's mission by addressing this key barrier through community-based, youth-led solutions to improve SRMNCAH outcomes.

5. Overall Goal and Specific Objectives

- Overall Goal

Reduction of maternal and adolescent mortality in Machinga District by improving the utilization of SRMNCAH services.

- Specific Objectives

  - To reduce perceived stigma related to SRMNCAH service-seeking among 500 youth in T/A Ngokwe by 50% within 15 months.

  - To increase the rate of youth referrals to partnered health facilities by 30% through established peer and gatekeeper networks.

  - To strengthen the capacity of 30 youth as "Tisankhe! Champions" to provide accurate SRMNCAH information and support.

6. Target Group / Beneficiaries

- Direct Beneficiaries (500)

Youth (15-24 years), with a 70% focus on adolescent girls and young women, in T/A Ngokwe, Machinga.

- Indirect Beneficiaries (2,000)

Parents, community members, and local health workers who will benefit from a more informed and healthier community.

- How they benefit

They will gain knowledge, confidence, and a supportive environment to access life-saving health services, leading to better health outcomes and life choices.

7. Project Activities

- Conduct formative research and baseline survey on knowledge, attitudes and practices.

- Organize 10 community dialogue sessions with Traditional Leaders (T/A Ngokwe, GVHs and elders).

- Recruit, train and deploy 30 youth as peer educators ("Tisankhe! Champions").

- Develop and disseminate youth-friendly IEC materials (posters, radio programs).

- Establish and formalize referral pathways with 3 local health facilities.

- Conduct quarterly monitoring visits and an endline survey to measure impact.

8. Expected Results / Outcomes

- Outputs

30 peer educators trained; 10 dialogue sessions held; 500 youth reached with IEC materials; 3 referral partnerships established.

- Outcomes: Measurable reduction in perceived stigma; increased service utilization at health facilities; sustained peer-support networks; enhanced community ownership of adolescent health issues.

9. Implementation Plan / Timeframe

The project will follow a clear 15-month timeline, tentatively structured into four key phases to ensure a logical and effective flow: Inception & Planning, Community Mobilization & Capacity Building, Core Implementation and Consolidation & Sustainability (January 2026 to March 2027)

10. Monitoring and Evaluation (M&E)

Progress will be tracked through regular data collection against key indicators, including the number of youth reached, changes in knowledge and attitudes from baseline to endline surveys, and service utilization rates from health facility records. This data will be collected by our M&E Officer through surveys, focus group discussions, and activity reports, ensuring we can measure our impact and make necessary adjustments throughout the project lifecycle.

11. Sustainability

To ensure benefits continue after the project, we will build local capacity by training youth peer educators who will remain in the community as lasting resources. Furthermore, we will secure buy-in from Traditional Authorities and the District Health Office from the outset, encouraging them to adopt successful project approaches into their ongoing plans and budgets for long-term impact.

12. Risk Assessment and Mitigation

| Risk | Likelihood | Mitigation Measure |
| --- | --- | --- |
| Resistance from community leaders | Medium | Early, respectful dialogue; involve them as partners, not targets. |
| Low participation from youth | Low | Use peer-to-peer recruitment; hold sessions in accessible, safe spaces. |
| Poor data quality from health facilities | Medium | Co-design simple data tracking tools with facility staff. |

13. Estimated Budget Summary

The total project cost is $80,000, strategically allocated to maximize impact. The majority of the budget, 75% ($60,000), is dedicated directly to program activities, including training, educational materials, community outreach, and monitoring. The remaining 25% ($20,000) covers essential personnel and administrative costs to ensure effective management and sustainability. A comprehensive budget breakdown will be provided in the full project proposal.

14. Donor Alignment / Justification

This project is fully aligned with CORE Group's SGSI purpose. It aims to advance SRMNCAH programming in Malawi by empowering a youth-led organization to design and implement a community-based solution to a key barrier. The project directly strengthens our organizational capacity and focuses on a high-impact intervention that will generate evidence for scaling, perfectly mirroring the grant's objectives.

15. Conclusion

The "Tisankhe!" Project offers a targeted, evidence-based and sustainable solution to one of the most significant barriers to SRMNCAH progress in Malawi. Mthunzi Trust possesses the community trust, youth-led perspective, and organizational commitment to ensure its success. We are eager to collaborate with CORE Group to refine this concept and are fully prepared to develop a detailed proposal to bring this vital initiative to life